## Slide 1
Make pharma knowledge RAG-ready
90-day pilot to cut hallucinations and compliance risk

## Slide 2
Decision request and outcomes
Unmanaged content drives 21–40% LLM errors and weak auditability, increasing compliance and IP exposure.
Why approve now: risk is in the data
Demonstrate <10% hallucinations and 50–70% faster insight retrieval on a curated corpus.
What you get in 90 days
Approve a 90-day unstructured-data readiness pilot to create a trusted RAG corpus for competitive intelligence and adjacent use cases, with measurable quality, risk, and speed improvements.

## Slide 3
Chart: 
| Slide decks | Study reports | CRM notes | Emails | Call recordings | SharePoint folders | Structured sources
Percent of CI | 25 | 20 | 15 | 12 | 6 | 2 | 20
Unstructured content is the risk surface
80% of competitive intelligence is trapped in unstructured assets (decks, study reports, CRM notes, emails, call recordings, SharePoint). Without ownership, deduplication, and metadata, RAG retrieval pulls stale or conflicting context, elevating compliance and IP leakage risk.

## Slide 4
Chart: 
| Unmanaged min | Unmanaged avg | Unmanaged max | Curated target
Hallucination rate (%) | 21 | 30 | 40 | 8
On unmanaged corpora, copilots show 21–40% error rates; curated corpora target <10% with eval gating and source grounding.
Hallucination rates
Quality work reduces LLM failure modes
Chart: 
| Competitive intelligence | PMR analysis | Patient journey planning
Unmanaged time (min) | 24 | 30 | 18
Curated time (min) | 8 | 10 | 6
Early adopters report 50–70% faster retrieval when RAG uses deduped, current, metadata-rich content with clear ownership.
Time to insight

## Slide 5
Inventory sources, owners, refresh cycles; pick initial high-value corpora.
1) Audit
Rate accuracy, completeness, currency; flag duplicates and conflicts.
2) Score
Dedup, consolidate, enrich metadata; assign ownership and refresh SOPs.
3) Curate
Define chunking, embeddings, vector DB schema, ranking and filters.
4) Design
Build 2–3 use cases; measure accuracy, hallucinations, satisfaction.
5) Pilot
Operationalize curation workflows, metrics, and continuous improvement.
6) Scale
Six-step RAG readiness playbook

## Slide 6
Top corpora
In scope
Out
AI readiness
Dedup+metadata
Chunk+embed+VDB
Owners+SOPs
All content
Manual review
Full rewrite
LLM fine-tune
New DMS
Sources
Scoring
Enrich
RAG
Operate
Scope boundaries for the pilot

## Slide 7
Audit sources, select corpora, confirm use cases, define success metrics.
Weeks 0–2
Move from unknown corpus quality to a measured, governed RAG-ready knowledge base with 4 gated phases and go/no-go criteria.
90-day pilot plan with milestones
Score content, map conflicts, prioritize curation backlog by risk and value.
Weeks 3–5
Curate and enrich; implement ownership and refresh workflow for pilot corpus.
Weeks 6–9
Build RAG pipeline and eval; report hallucination rate and retrieval speed.
Weeks 10–13

## Slide 8
PO
Role
Need
Data eng
ML eng
Compliance
Named + time
Access+pipelines
Eval+tuning
PII/GxP rules
PO
Data eng
ML eng
Compliance
Resource requirements

## Slide 9
Risk map and mitigations
Regulated or sensitive content in corpus. Mitigate with classification, access controls, PII redaction, and audit logs.
High impact, high likel.
Duplicates and stale decks degrade retrieval. Mitigate with dedup, recency scoring, and refresh cadence enforcement.
Low impact, high likel.
Conflicting “truth” sources cause wrong decisions. Mitigate with authoritative source tags and conflict resolution workflow.
High impact, low likel.
Minor metadata gaps. Mitigate via minimum metadata schema and automated enrichment where possible.
Low impact, low likel.

## Slide 10
Chart: 
| Competitive intelligence | PMR analysis | Patient journey planning
Baseline time to insight (min) (LHS) | 24 | 30 | 18
Target hallucination rate (%) (RHS) | 8 | 8 | 8
Pilot success metrics (targets)
Pilot is successful only if we hit measurable targets:
50–70% faster insight retrieval on selected corpora
<10% hallucination/error rate on a defined eval set
Audit-ready provenance: citations, timestamps, owner, and confidence metadata

## Slide 11
Chart: 
| Pilot cost ($k) | Estimated annual savings ($k) | Estimated payback (months)
Illustrative ROI | 250 | 900 | 3
ROI model and required inputs
Value case combines time-to-insight savings and risk avoidance. Provide inputs to finalize ROI:
[NEEDS YOUR INPUT] approved pilot cost and run-rate scaling cost
[NEEDS YOUR INPUT] analyst hours/week on competitive intel retrieval
[NEEDS YOUR INPUT] fully loaded labor rates and audit findings cost assumptions

## Slide 12
Governance and decision rights
RAG corpus rules
Data architecture council
Domain content stewards
Standard
Owners

## Slide 13
Decision and kickoff
Sponsor decision, unblock access, and assign a single accountable product owner for the pilot outcomes.
CDO + AI lead
Decision date to enable a clean start and complete the pilot within the next quarter window.
By Feb 20, 2026
Product owner, data engineering, ML engineering, compliance signoff, and IT access to selected repositories.
Named core team
Confirm pilot corpora + 2–3 use cases (e.g., competitive intelligence, PMR analysis, patient journey planning) and agree on target metrics: <10% errors and 50–70% faster retrieval.
Approve the 90-day pilot

## Slide 14
Implementation details to finalize during design
Chunking strategy: policy for chunk size, overlap, and section-aware splitting
Embedding approach: model selection criteria, normalization, update strategy
Vector DB design: namespace strategy by corpus, metadata indexes, retention rules
Retrieval controls: ranking signals, filters (recency, authority), citation requirements
Evaluation harness: golden Q&A set, hallucination taxonomy, acceptance thresholds
Compliance controls: classification labels, access tiers, audit logging requirements
Open items:[NEEDS YOUR INPUT] approved cost and ROI assumptions to populate the ROI slide with final numbers
Technical appendix (RAG details)